## Sheet1
Objective | Target No. | Target and commentary 2020 - 2021 | Status
1. Broaden the definition of sustainability for major corrections projects | 1.1 | Achieve IS Design and As-Built v2 certifications each with a minimum of 50 points awarded (Silver +10) The Chisholm Road project is pioneering the Infrastructure Sustainability Council of Australia’s IS Design and As-Built v2 certification rating scheme, currently in beta testing. Work towards this target is ongoing through the construction phase. The IS Rating Scheme (IS) is Australia and New Zealand’s only comprehensive rating system for evaluating sustainability across the planning, design, construction and operational phases of infrastructure programs, projects, networks and assets. The project is currently on track to achieve a silver rating with every effort being made to achieve more. | In progress
| 1.2 | Develop objectives, targets, plans, processes and knowledge that can be shared with future Victorian corrections projects (and other State and Territory counterparts). The Department of Justice and Community Safety has already been able to meet this target. The department reviewed its Ecologically Sustainable Development guidelines in light of learnings from the project so far and presented these findings with Whole-of-Victorian Government counterparts to strengthen knowledge across the public sector. Guidelines and processes will continue to be reviewed as works progress to accommodate future learnings. | Meeting or exceeding target
| 1.3 | Clearly define and adhere to processes regarding governance, risk management and economic appraisal of options. Work towards this target is ongoing through the construction phase. The department has to date been successful in developing and following strong frameworks which are consistent with Australian and New Zealand Standards and include processes that effectively manage risk. Currently, the focus is being given to ensure that reporting is accurate and timely. | In progress
2. Minimise operational greenhouse gas emissions | 2.1 | Reduce grid energy consumption in operation by at least 15% compared to standard practice, including solar photovoltaics, with best-practice sub-metering and commissioning. The project is on course to meet this target. Current modelling indicates that the Chisholm Road project will comfortably meet a reduction in grid energy consumption of 15%. This is currently being accomplished through passive design, an efficient central plant, solar photovoltaics and panels, as well as low energy, LED lighting. | Meeting or exceeding target
| 2.2 | Design in upgrade pathways for stationary batteries, the expansion of renewable generation capacity, and electric vehicle charging. The project is on course to meet this target comfortably with considerations given for capacity improvement at a later point. A solar farm is currently located outside the secure perimeter and can be expanded in the future. The main electrical switchboard is also designed to accommodate future solar farm expansion and/or battery installations. As well as this, a conduit has been specified to serve Electric Vehicle charging stations in anticipation of future demand. | Meeting or exceeding target
| 2.3 | Minimise the use of fossil fuels during operation as far as practicable, and design in upgrade pathways which allow fossil fuel use to be eliminated altogether in future. The project is on course to meet this target. The consumption of natural gas has been minimised through the efficient use of the central plant. The central heating hot water system has been located in the central utilities compound with heating water distributed throughout the site via underground pipework. This arrangement is flexible for future fuel switching, namely, an electric or hydrogen central heating plant. | Meeting or exceeding target
| 2.4 | Select refrigerants with global warming potentials as low as practicable, with automatic leak detection and recovery systems for chillers containing conventional refrigerants. The project is on track to meet this target. The department is proud to report that all refrigerants chosen have global warming potentials as low as practicable or otherwise meet the required specifications. | Meeting or exceeding target
3. Minimise potable water consumption | 3.1 | Reduce mains water consumption in operation by at least 40% compared to standard practice, including maximising the harvesting and reuse of stormwater. The project is currently set to exceed this target. The department is proud to report that total water saving is currently 49% below standard practice. Whole site water modelling indicates that 37% of water saving is being achieved through the specification of efficient fixtures and fittings, and a low water irrigation system. A further 12% reduction of site usage is being achieved through supplementing non-potable water uses such as toilets, washdown, and irrigation with recycled water from the site-wide capture and treatment system. | Meeting or exceeding target
| 3.2 | Minimise mains water consumption during construction by at least 30% compared to standard practice, via efficiency and stormwater harvesting and re-use (i.e. without trucking recycled water). The project is on track to achieve this target. To achieve this a 60kL tank is being utilised by water trucks for dust suppression and other uses. There are also 30kL tanks as part of the main compound setup. The overall volume of water usage is being progressively captured to ensure water consumption continues to be minimised throughout the construction phase. | Meeting or exceeding target
4. Optimise safety and wellbeing for all users | 4.1 | All staff areas designed for wellbeing and safety, with an appropriate number of areas that also support wellness and enjoyment. The health and wellbeing of staff are taken very seriously and the project is on track to meet this target. Consideration at the design stage of the project focussed on the materiality of staff only areas to enable users to feel connected to the outside environment and feel less institutional in the context of existing within a prison. As part of this, all staff areas have access to a nearby courtyard for outdoor use. | Meeting or exceeding target
| 4.2 | All prisoner areas designed for safety, with specific consideration given to recidivism minimisation through a non-institutional aesthetic, cultural sensitivity and prisoner wellness. The project is on track to meet this target comfortably. At the design phase strong importance given to prisoner safety and wellbeing. Examples of this include the layout of prisoner accommodation areas to enable users to feel connected to the outside environment with the choice of materials. Where safety issues have been raised, materials that look similar have been used, such as in the use of timber. Key research which has informed the project has shown that materials that represent nature still have the same effect. The Department is also proud that appropriate sensitive design considerations were given to the cultural centre on-site. The Department undertook consultation with the Traditional Owners to develop a collaborative approach to its design. Landowners influenced what was included in the courtyard and the colours and design of the interiors. | Meeting or exceeding target
| 4.3 | Climate change projections regarding greenhouse gas concentration trajectory (2050 @ RCP 6.0) to be accounted for in the design of cooling systems, architecture and landscaping. The project is on track to meet this target. This is being achieved through practices such as planting larger varieties of trees near large windows in accommodation blocks which will create shade and therefore reduce the heat gain from the sun. Operable ventilation in cell windows has also been included for temperature management. | Meeting or exceeding target
5. Minimise impact to surrounding community & environment | 5.1 | Minimise the impact of artificial lighting, noise, visual bulk, and increased traffic on the immediate area as far as practicable. Once completed the project will have met this target comfortably. Action to this point has included daylight calculations to all office areas, making sure that the design and layout meet the standards for natural light to workplaces, thus reducing the need for artificial light. Skylights have also been placed in long corridors which have no external walls. Focus on the design of acoustics has also been incorporated to reduce noise between rooms and spaces, reducing overhearing of confidential conversations, as well as reverberation in large spaces. This will not only contribute to minimising the impact on the surrounding community & environment but improve staff health and wellbeing. | Meeting or exceeding target
| 5.2 | Minimise the environmental harms and social risks associated with the procurement of construction materials – at least 5% by value of all products procured should have ISCA-recognised environmental labels. The project is on track to meet this target. Processes in place require that all proposed products and materials for the project are subject to review and approval via a formal sample submission process making this target more easily attained. This review also addresses and accounts for the associated sustainability aspects. The usage, including quantity and value, is being progressively captured and monitored throughout the construction phase. | Meeting or exceeding target
| 5.3 | Of the 90% local content required by the Local Jobs First Policy, at least 50% should be Victorian, and 10% local. The project is currently exceeding local content targets under the Victorian Government’s Local Jobs First Policy with over 92% of labour and materials used during construction sourced within Australia and New Zealand. A significant number of contracts have been awarded to companies operating within the Geelong area, and in Victoria more broadly, including 30,000 hours allocated to Victorian’s living in areas of high unemployment. The project’s focus on maximising the use of locally-milled steel has resulted in further progress towards exceeding local content requirements in the 2020-21 reporting period. | Meeting or exceeding target
| 5.4 | Protect and enhance biodiversity through the siting of buildings and infrastructure, construction methodologies, active revegetation, and the protection of local watercourses. Work is continuing during the project to ensure that biodiversity is protected and enhanced and that this target is met by completion. Site selection and project designs avoided impacts to significant biodiversity and habitat, with future landscaping and water reuse to increase local biodiversity values. Environmentally sensitive areas including watercourses are protected through the implementation of approved Environmental Management Plans during construction. Procedures are also in place to immediately stop works, and report non-compliance to relevant authorities if needed. The project is also investigating potential impacts on offsite biodiversity. | In progress